## Traceability Matrix
Ngā Tai e Rua Pā — Requirements Traceability Matrix
Every user story from the original brief, mapped to the acceptance test(s) that verify it. Status: Covered = a real, shipped feature verifies this story. Partial = the feature exists but doesn't fully match the story's wording. Not Implemented = no corresponding feature was found in the codebase.
Story ID | User Story | Covered by | Status | Notes
S1 | As an arriving marae user I want to be shown how to turn on the gas | AT-01 | Covered
S2 | As an arriving marae user I want to be shown how to turn on the water | AT-01 | Covered
S3 | As an arriving marae user I want to know how to connect to the wifi | AT-01 | Covered
S4 | As an arriving marae user I want to know who to contact if I have a question or a problem | AT-01, AT-10 | Covered | Contact info appears both in the Marae Guide's content and on the public Contact Us page.
S5 | As an arriving user I want to know how to turn on the lights | AT-01 | Covered
S6 | As an arriving marae user I want to know the rules and regulations for the Marae | AT-04 | Covered | Implemented as a collapsible panel inside the Marae Guide, not a standalone page.
S7 | As an arriving Marae user I want to know which buildings are for what and where (MAP) | AT-06 | Covered
S8 | As an arriving marae user I want to know about the health and safety of the marae | AT-03 | Covered | Implemented as a collapsible panel inside the Marae Guide, expanded by default.
S9 | As an arriving marae user I want to know the emergency evacuation points | AT-05 | Covered | Its own subpage (/arrival/emergency) with real exits/assembly point/first aid info.
S10 | As an arriving marae user I want to know what equipment there is that is available | AT-01 | Covered
S11 | As an arriving user I want to know how to turn on the fans/air conditioning | AT-01 | Covered
S12 | As a user of the marae, I want to be able to log in to my account | AT-07 | Covered
S13 | As a marae user with an approved booking, I want to be able to see onboarding instructions/content | AT-02 | Covered | This is the access-control rule itself: only an approved, currently-active booking unlocks the guide.
S14 | As a marae user with an approved booking, I want to be able to find instructions on using equipment | AT-01 | Covered
S15 | As a user, I want to be able to sign up | AT-08 | Covered
S16 | As a marae user, I want to be able to contact management / make a report for issues | AT-09 | Covered
S17 | As a marae user, I want to be able to easily find any content (search bar, context based grouping) | AT-11 | Covered
S18 | As an admin, I want to be able to add new content in a selected area | AT-12 | Covered
S19 | As an admin I want to be able to delete content from a selected area | AT-12 | Covered
S20 | As an admin I want to be able to move content | AT-12 | Covered
S21 | As an admin I want to be able to copy content | AT-12 | Covered
S22 | As an admin, I want to be able to modify content of a selected area | AT-12 | Covered
S23 | As an admin I want to be able to select which user types can view certain content | AT-12 | Covered
S24 | As a booker, I want to be able to request a booking | AT-13 | Covered
S25 | As a booker I want to receive confirmation of if my booking has been accepted | AT-15 | Covered
S26 | As a booker I want to be able to see what days and times the marae is available for hire | AT-14 | Covered
S27 | As a booker I want to be able to review and confirm my booking | AT-13 | Covered | Implemented as a single booking-request form (the entered details are shown back on My Bookings afterward), not a separate review/confirm screen.
S28 | As a booker I want to be able to fill in lots of information so that the admin can decide to approve or reject my booking request | AT-13 | Covered | Decision is made by the manager role, not admin -- see note on S31/S34/S35.
S29 | As a booker of the marae I want to be able to view information about the marae | AT-10 | Covered
S30 | As a booker I want to be able to cancel my booking | AT-17 | Covered
S31 | As an admin I want to be able to view the details of any booking | AT-18 | Covered (role mismatch) | Implemented, but exclusively under the 'manager' role, not 'admin'. Admin has no booking access at all in the shipped system -- see the role-mismatch note below the table.
S32 | As a booker I want to be able to receive notifications about the status of my booking request | AT-15 | Covered
S33 | As a booker I want to be able to modify my booking | AT-16 | Covered
S34 | As an admin I want to be able to confirm or reject a booking and inform the booker of the results | AT-19 | Covered (role mismatch) | Same role mismatch as S31 -- this is a manager-only action in the shipped system.
S35 | As an administrator I want to be able to view a list of pending bookings | AT-18 | Covered (role mismatch) | Same role mismatch as S31.
S36 | As a caretaker I want to be able to see the inventory of equipment as well as the maintenance of it | AT-24 | Covered | Implemented as a lean equipment list (name + condition) under /caretaker/equipment -- caretaker/admin can add, edit and remove items; manager has read-only access. Scoped deliberately: no quantity tracking or scheduled-maintenance dates, since the client's priority was just knowing what exists and its condition.
S37 | As a caretaker I want to be able to find/search for content for a particular task | AT-21 | Covered
S38 | As a caretaker I want to be able to access a calendar which will tell me about holidays and availability | AT-22 | Covered | Confirmed the story's intent was always booking availability, not separate public-holiday data -- the shared caretaker calendar's booking overlay fully satisfies it. No code change; this is a reclassification from 'Partially covered' once the wording was clarified.
S39 | As a caretaker I want to be able to see checklists and other content for specific or different tasks | AT-20 | Covered
S40 | As a caretaker I want to be able to see the overall schedules of tasks for the next x amount of weeks | AT-22 | Covered
S41 | As a caretaker I want to be able to get notified for upcoming scheduled tasks | AT-25 | Covered | Implemented as an in-app 'Upcoming Tasks' panel on the caretaker and manager dashboards, surfacing today/tomorrow's incomplete tasks from the existing shared task list -- chosen over email/cron reminders as the quicker, lower-risk option for the deadline.
S42 | As a caretaker I want to be able to add/delete/modify the schedules of tasks for the future | AT-23 | Covered
Role-mismatch note (S31/S34/S35): the original stories say "admin", but during development a new "manager" role was introduced and ALL booking management (view/approve/deny/pending queue) moved to it -- admin was deliberately reduced to content-management only. The capability fully exists and is tested (AT-18, AT-19); it just sits under a different role name than the brief specifies. Flag this to the client/marker as a deliberate scope change, not a missed requirement.

## Acceptance Tests
Ngā Tai e Rua Pā — Acceptance Test Scripts
Run each one live with (or in front of) the client. Fill in Result / Signed off by / Date as you go -- that's your acceptance evidence for handover. 'Covers' lists which user story IDs this test verifies (see the Traceability Matrix tab).
AT ID | Scenario | Covers | Given | When | Then | Result | Signed off by | Date
AT-01 | Marae Guide shows practical stay instructions | S1,S2,S3,S4,S5,S10,S11,S14 | A member has an approved, currently-active booking and opens the Marae Guide. | They browse the Arrival / General / Leaving content groups. | Instructions for gas, water, wifi, lights, and fans/air-con are all present and correct; the available-equipment info (including the Combi oven recipe) is there; contact info for questions/problems during the stay is listed.
AT-02 | Marae Guide access requires an approved booking | S13 | One member has no booking at all; another has an approved booking whose dates cover today. | Each opens the Marae Guide (/arrival). | The member with no booking sees an access-denied message, not the guide content. The member with the active approved booking sees the full guide.
AT-03 | Health & Safety information is shown | S8 | A member with Marae Guide access opens the guide. | The page loads. | The Health & Safety panel is visible and expanded by default, showing the real content (prohibited items, fire/evacuation procedure, first aid locations, earthquake procedure).
AT-04 | Rules & Regulations information is shown | S6 | A member with Marae Guide access opens the guide. | They expand the (collapsed-by-default) Rules & Regulations panel. | The real rules/regulations content for the marae is shown.
AT-05 | Emergency evacuation information is shown | S9 | A member with Marae Guide access. | They navigate to the emergency info subpage. | Real evacuation facts are shown: exits, assembly point (front carpark), first aid kit locations, and emergency contact numbers.
AT-06 | Map shows what each building is and where | S7 | Any visitor, logged in or not. | They open the Map page. | The marae's map image displays with labelled pins; selecting a pin shows which building/area it represents.
AT-07 | Login | S12 | An account already exists. | The user enters the correct email and password on the Login page. | They're logged in and redirected to their role's home page.
AT-08 | Sign up | S15 | A new, not-yet-registered email address. | The user fills in the sign-up form and submits. | An account is created with the 'member' role and the user is logged in immediately.
AT-09 | Report an issue / contact management | S16 | A logged-in user has a problem to report. | They submit it via Report an Issue. | The issue is created with status 'open'; a caretaker, manager, or admin can see it on their Issues page and change its status (e.g. to 'resolved').
AT-10 | Public information pages about the marae | S4,S29 | Any visitor, logged in or not. | They browse Home, History, Facilities, Events and Contact Us. | Each page shows real content (not placeholder text), including History's land-purchase/Trust Charter story and Contact Us's real contact names and numbers.
AT-11 | Finding content via search and category grouping | S17 | A logged-in user is on the Content Library page. | They type a search term and/or select a category tab. | Only items whose title/body match the search term remain, and/or only items in the selected category are shown.
AT-12 | Admin content management (add / edit / move / copy / delete / restrict by role) | S18,S19,S20,S21,S22,S23 | An admin is logged into Content Manager. | They create a new content item, edit its text, move it to a different category, copy it, restrict it to specific roles via 'visible to roles', then delete the original. | Each action succeeds and is reflected immediately: the new item appears; edits update the displayed text; the moved item appears under its new category; the copy appears with a '(Copy)' suffix; the restricted item is hidden from roles not selected; the deleted item disappears.
AT-13 | Submitting a full booking request | S24,S27,S28 | A logged-in member with no conflicting booking. | They fill in dates, purpose, booking type, area and the whakapapa question, and submit. | The booking is created with status 'pending'; the submitted details are visible back to them on My Bookings for review.
AT-14 | Seeing availability before requesting a booking | S26 | Other approved/pending bookings already occupy some dates. | A member opens the booking calendar while making a request. | Those already-booked dates are shown as unavailable/tentative; open dates remain selectable.
AT-15 | Booking status notifications | S25,S32 | Two pending bookings exist. | The manager approves one and declines the other. | The first requester receives an approval/confirmation email and sees 'approved' on My Bookings; the second receives a decline email and sees 'denied'.
AT-16 | Modifying an existing booking | S33 | A member has a booking of their own that hasn't been cancelled. | They edit its dates/purpose/type and save. | The booking updates with the new details and its status reverts to 'pending' for re-review.
AT-17 | Cancelling a booking | S30 | A member has a booking of their own. | They cancel it. | Its status becomes 'cancelled' and it can no longer be edited.
AT-18 | Viewing the pending queue and any booking's full details | S31,S35 | Several bookings exist in different statuses. | A manager opens Manager -> Bookings. | Pending bookings are clearly identifiable; selecting any booking shows its full details, including the requester's name and contact details.
AT-19 | Confirming or rejecting a booking | S34 | A pending booking exists. | A manager sets it to 'approved' in one case and 'denied' in another, optionally with a note. | Each booking's status updates accordingly and the requester receives the matching email.
AT-20 | Caretaker checklists and tutorials for tasks | S39 | A caretaker is logged in; checklists and tutorial content already exist. | They open Checklists and Tutorials. | The Opening/Closing checklists and tutorial content items are visible and usable for reference during a task.
AT-21 | Searching caretaker content for a task | S37 | A caretaker is on the Tutorials page with several tutorials present. | They type a search term. | Only tutorials whose title/body match the search term remain visible.
AT-22 | Task schedule for the coming weeks, with booking overlay | S38,S40 | A caretaker has added several scheduled tasks across the next few weeks, and an approved booking covers part of that period. | The caretaker opens the Task Schedule/Calendar. | Tasks for the coming weeks are visible; the day(s) with an active booking are visibly marked -- this is the 'availability' half of S38, confirmed as its intended meaning (see Traceability Matrix).
AT-23 | Adding, editing and deleting scheduled tasks | S42 | A caretaker is on the Task Schedule. | They add a new task, edit an existing one, mark one complete, and delete one. | Each change persists and is visible to the manager too (it's a single shared schedule, not per-caretaker).
AT-24 | Equipment inventory (add / edit / delete, manager read-only) | S36 | A caretaker is logged in on the Equipment page; a manager is logged in on the same page. | The caretaker adds a new item with a name and condition, edits an existing item's condition, then deletes an item. The manager views the same page. | Each caretaker change persists immediately and is visible to the manager; the manager sees the full list but has no add/edit/delete controls.
AT-25 | Upcoming Tasks panel surfaces today/tomorrow's work | S41 | The shared task list has one task due today, one due tomorrow, one due next week, and one due today but already marked complete. | A caretaker (and separately, a manager) opens their dashboard. | The Upcoming Tasks panel lists only the today and tomorrow tasks that aren't completed, labelled accordingly and sorted by time; the next-week task and the completed task are not shown.

## Additional Tests
Additional Acceptance Tests — beyond the original 44 user stories
These verify real, client-requested functionality that was added during development and doesn't map to any of the original 44 stories (guest/QR-code access, and the caretaker permission boundary). Keep them as evidence of what else was built and tested, clearly separate from the story-traceable set above.
AT ID | Scenario | Covers | Given | When | Then | Result | Signed off by | Date
AX-01 | Guest reaches the Marae Guide via a per-booking share link | (not in original stories) | A booking is approved and currently active; the member has generated its share link/QR from My Bookings. | An unauthenticated guest opens that link in a private/incognito window. | The Marae Guide loads with no login required.
AX-02 | Generic signage QR code only works while a booking is on-site | (not in original stories) | The fixed 'Guest access for signage' link is opened once while a booking covers today, and once while none does. | A guest opens the fixed signage URL in each case. | While a booking covers today: the guide loads normally. With none covering today: a clear 'not currently available' message is shown instead.
AX-03 | A caretaker cannot edit content outside their own Tutorials page | (not in original stories) | A caretaker is logged in. | They attempt to edit or move a content item belonging to another public page (e.g. Home or History). | The request is rejected (403 Forbidden); the other page's content is unchanged.